## Planning
Task no | Task details | Sub task | Team members | Status | Remarks
PEN1001 | GPRS data upload | Connection checking
Code cleanup
Data upload (JSON)
indicator fault upload
store data offline when no connection
Button fetch
Configuration fetch
Timeout function
|  | MQTT protocol |  |  | Optional
|  | MQTT Hardware |  |  | Optional
PEN1002 | Power Source monitoring | ac voltage
ac current
ac power
dc voltage
dc current
dc power
PEN1003 | Flash memory | Read chip info
Read data
write data
erase sector
erase block
erase chip
create pages for storing data, configuration, fault logs, data logs
PEN1004 | Server Side scripting | Storing data in JSON format
Multi device information in a single page
No data available info
configuration of each devices
individual indicator info
Fault log page
History page
Action button working
New device registration
PEN1004 | RTC | Read time
Read Date
Set Time
Set Date
Set Alram
PEN1004 | Display | LCD Setting
LCD Command
LCD Data
write data
Clear Display
Animation effects

## Working and assign tasks
(Week Sprint 1) 28/Jun/2021 Team lead Sunil, Khaleel Tech Lead | [5 empty] | Time Sheet
|  | Sub Task | Team Member | Complexity Level | Remark | Sunil | Kheeel | Arun | Rahamath
Objective 1 | GPRS Data
KR1 | GPRS Intialization | Detect SIM card | Sunil | High |  | 8 |  |  |  | Khaleel
|  | Detect N/w | Sunil | Medium |  |  | 3 |  |  | Sunil
|  | Initialise GSM NW | Rahamath | Low |  |  | 2 |  |  | Rahamath
|  | Initialise GPRS | [7 empty] | Arun
Make GPRS Bearer Connection
Link HTTP connection
Uplaod the Data
Close HTTP connection
KR2 | GPRS Response | Read the response | [7 empty] | High
|  | Parse the response | [7 empty] | Medium
KR3 | Server Application | Creat PHP scripit to read URL | [7 empty] | Low
Fetch Data from URL and store DB
Send success response to Device
Send customizsed response to device
KR4 | Web Application | Create PHP scrpit to read data from DB
KR4_1 |  | HTML and CSS to desing the UI
KR4_2 |  | Customizsed Template
KR4_3 |  | Different Login user
KR4_4 |  | Admin should be able creat device
KR4_5 |  | Admi can assing devices to each user
KR4_6 |  | User can read/write only his device
KR4_7 |  | User rights to configured read and Write
KR4_8 |  | Device Confguration 1. Device ID 2. Device Location 3.Device Name 4.Device Capablities etc.
Objective 2 | Read Parameter
KR1 | Memory | Memory Intitilasation
KR1_1 |  | Memory Configuration
KR1_2 |  | Memory read
KR1_3 |  | Memory Write
KR1_4 |  | Memory related APIs
KR2 | Internal Temp sensor | Intiiaise the temp sensor
Intilaise internal ADC
read Temperature
Store Temperuatre with time
KR3 | Power Parmeter | Intialise the AC sensors
Read AC Volatage values
Read AC current values
Store w.r.t time
Intialise the DC sensors
Read DC Volatage values
Read DC current values
Store w.r.t time
KR4 |  | Intialise the RTC
Read time
Read Date
Set Time
Set Date
Set Alarm
Objective 3 | Device User Interface & Security
KR1 | LCD 16x2 | Initilaisation
Command write
Data Write
Clear Display
Animation display
KR2 | Key pad 4 Buttons | Initilaisation
Read Keys
Create Menus
Navigate Menu
Error Resets
KR3 | LEDs | Initilaisation
LED sequencing for Indication
LED Animation
LED OFF
LED ON
KR4 | RTC | Display Date and Time
KR5 | LCD 16x2 | Display error Messages
Power Consumptions
KR6 | Device Security | Initlaisation of GPIO
Monitor the GPIO open
Raise alram Buzzer or LED
Display on LCD
Send Secuirty breach to Server
Send SMS Alert to User
Authorise access for secured access
Shut down the device incase of security breach
Objective 4 | Faults & Log
KR1 | Faults | Overload
Short Circuit
GSM NW issues
GPRS No connections
ADC not working
Sensor not wokring
Key Pad fault
LCD fault
LED fault
Flash Memory error
RTC Error
Send communication Failed
Set voltage AC threshold overshoot
Set voltage DC threshold overshoot
Set Current AC threshold overshoot
Set Current DC threshold overshoot
All to be logged in flash memory with date and Time
KR2 | History Log | Log every data that is send to Sever
Log for three months rolling period.
Memory full and roll back time to be logged seperatley for every roll over and communicate with the server.
Objective 5 | Communication with Server
KR1 |  | Uploading of Parmeters to server
Repose from Server
Set date and time Request
Set threshold Request
Request history Log
Request for Fault Log
Request for SMS with recent data
Shut down device from Server
On the device from Server
Request status of keys
Request Configuration from Server
Incase no NW restart the GMS modem.

## Software Planning
(Week Sprint 1) 28/Jun/2021 Team lead Sunil, Khaleel Tech Lead
|  | Sub Task | Team Member | Complexity Level | Remark | Arun | Rahamath
Objective 1 | Pendios Dashboard
KR1 | Login Page | UserName and Password Fields |  | High |  |  |  | Khaleel
|  | Login Button redirect to dashboard |  | Medium |  |  |  | Sunil
|  | Username and Password Validation |  | Low |  |  |  | Rahamath
|  | if username and password matches the query it redirect to Next page | [5 empty] | Arun
session get started and redirect to next page
KR1_1 | Forgot Password | New password and confirm password |  |  |  | 2
After creating new password data get updated in database
KR2 | User Dashboard | Displaying Username and Device Id | [5 empty] | High
KR2_1 | Displaying of Device value
| Ac & Dc voltage | Display the Ac & Dc voltage respect to device id | [5 empty] | Medium
| Ac & Dc Current | Display the Ac & Dc Current respect to device id
| AC & Dc Power | Display the Ac & Dc Power respect to device id
KR2_2 | Updated Time | Display the Updated time respect to device id
KR2_3 | Status of Device | indicating LED Short Circuit,Shutdown ,Overload,Tampering and Health
indicating status of device green for Good
indicating status of device red for Bad
KR2_4 | Graph | Display the AC & Dc voltage vs Time in Bar chart
Ac voltage graph start from 0 to 250v
Dc voltage from 0 to 25 v
Getting device data from db and fetching according to graph are Plot
Objective 2 | Pendios Configuration
KR1 | Configuration | configuration the user data with the device
| Device id | Device id Configuration
| Mobile No | Mobile No Configuration
| auth code | Auth code Configuration
| server link | server Link Configuration
| apn | Apn Configuration
| Username | Username Configuration
| password | password Configuration
| location | location Configuration
| address | Address Configuration
KR1_1 | Submit Button | Submit button store the value into data base
After Submitted data Store in DB
Objective 3 | Pendios History
KR1 | Export Button | it download the data into excel Format |  |  |  | 1
fetch the data from DB and Download in Excel Sheet
KR2 | Print Button | Download data into pdf format
fetch data from DB and download in the pdf file
KR3 | Data Table | it fetch the data from DB and Display in dashboard |  |  |  | 2
KR3_1 | search | we can search value in the data table
| Filtering option | Ascending and descending order in a particular column
| Number of Rows | displaying rows as required
ADMIN Pendios
Objective 1 | Admin Login |  |  |  | Completed |  | 1
KR1 | Login Page | UserName and Password Fields
Login Button redirect to dashboard
Username and Password Validation
if username and password matches the query it redirect to Next page
session get started and redirect to next page
KR2 | Admin Dashboard | Drop down option |  |  | under process alignment issue with the dashboard |  | 2
selecting the device id from Drop down List
selected device id will fetch the user device data from DB
Fetch entire data from device id and display into the dashboard
Objective 2 | Configuration |  |  |  | partially completed need to implement and work on frontend part |  | 1
KR1 | Configuration | configuration the user data with the device
| Device id | Device id Configuration
| Mobile No | Mobile No Configuration
| auth code | Auth code Configuration
| server link | server Link Configuration
| apn | Apn Configuration
| Username | Username Configuration
| password | password Configuration
| location | location Configuration
| address | Address Configuration
Objective 3 | Actions |  |  |  | partially completed need to implement in the dashboard |  | 1
KR1 | send_sms_on_demand | if button is click value get update to DB It Show the colour according to value updated
if value 1 green colour ,if value 0 red Colour
KR2 | Update_server_on_demand | if button is click value get update to DB It Show the colour according to value updated
if value 1 green colour ,if value 0 red Colour
KR3 | Authorise access | if button is click value get update to DB It Show the colour according to value updated
if value 1 green colour ,if value 0 red Colour
KR4 | Shutdown Device | if button is click value get update to DB It Show the colour according to value updated
if value 1 green colour ,if value 0 red Colour
Objective 4 | Faults & Log
KR1 | Faults | need to discuss with Khaleel and Sunil Sir
Objective 5 | User Creation | admin should create the credentials for the user |  |  | partially completed |  | 3
|  | if the admin creates user credentials it dynamically creates a table in the db with the user credentials |  |  | working with the frontend

## Task Sheet
Objective 1 | GPRS Data
KR1 | GPRS Intialization | Detect SIM card | Pending
|  | Detect N/w | Pending
|  | Initialise GSM NW | Done
|  | Initialise GPRS | Done
|  | Make GPRS Bearer Connection | Done
|  | Link HTTP connection | Done
|  | Uplaod the Data | Done
|  | Close HTTP connection | Done
KR2 | GPRS Response | Read the response | Done
|  | Parse the response | Done