## Khaleel
2021-06-16
Objective CAN
Task No | Task Name | Complexity level | Team Member | Status | Remarks
Task 1 | AWS role creation and rule engine | HIGH | Khaee1 | In Progress | working on role creation with esp32
Task 2 | Currently working on pendios dashboard functionalities with Arun and Rahamath | High | Arun, Rahamath and Khaleel | In Progress | Action page is under progress
Task 3

## Arun
Date | Task No | Task Name |  | Complexity level | Team Member | Status | Remarks
16/6/2021 | Task 1 | pendios dashboard |  | middle | arun | in progress | db table- history page -completed
2021-06-17 | task2 | pendios dashboard |  | middle | arun | in progress | icon,title,stausbutton
Week | 2021-06-28 | 2021-07-03
Sno | Task | Descriptions | Complexity Level | Status | Remark | Timeline In hr
1 | Dash Board | Action Button | Middle | Completed | Need help Road Block | 7
2 | [5 empty] | 4

## Sunil
2021-06-16
| Task No | Task Name | Complexity level | Team Member | Status | Remarks
| Task 1 | CAN | HIGH | Sunil | In Progress

## Rahamath
2021-06-16
Objective CAN
Date | Task No | Task Name | Complexity level | Team Member | Status | Remarks
17-jun | Task 1 | Fernhill website | middle | Rahamath | almost complete | Upload to fernhill server is pending
Task 2
Task 3