## Khaleel
Objective CAN
2021-01-07 | Task No | Task Name | Complexity level | Team Member | Status | Remarks
| Task 1 | AWS role creation and rule engine | HIGH | Khaee1 | Completed | working on role creation with esp32
| Task 2 | Currently working on pendios dashboard functionalities with Arun and Rahamath | High | Arun, Rahamath and Khaleel | In Progress | Almost completed, admin side configuration and group creation in progress
| Task 3 | Working on calyxtract Orientation module flow diagram | High | Khaleel | completed
| Task 4 | gsm at commands for signal quality, sim detection, module ready and up | medium | khaleel | completed | Done
| Task 5 | XDS110 debugger program custom board | medium | khaleel | in progress
| Task 6 | pendios board bringup | medium | khaleel | in progress
| Task 7 | working on calyxtract touchpanel design for testing | high | khaleel/rahamath | in progrss | Frontend is given to rahamath, he is busy finishing admin panel of pendios
| Task 8 | Working on calyxtract Orientation module programming | high | Khaee1 | in progress | Almost complted, should be tested on site and do the suitable changes

## Arun
Date | Task No | Task Name | Complexity level | Team Member | Status | Remarks
16/6/2021 | Task 1 | pendios dashboard | middle | arun | in progress | db table- history page -completed
2021-06-17 | task2 | pendios dashboard | middle | arun | in progress | icon,title,stausbutton

## Sunil
2021-06-16
DATE | Task No | Task Name | Complexity level | Team Member | Status | Remarks
| Task 1 | CAN | HIGH | Sunil | In Progress
2021-06-30 | Task 2 | Working on Pendios Project flow diagram and Programming | HIGH |  | In Progress
2021-07-01 | Task 3 | Internal ADC with CAN(Master is Tx and Slave is RX) | Medium |  | Done

## Rahamath
2021-06-16
Objective CAN
Date | Task No | Task Name | Complexity level | Team Member | Status | Remarks
17-jun | Task 1 | Fernhill website | middle | Rahamath | almost complete | Upload to fernhill server is pending
| Task 2 | Pendios | middle | Rahamath | New login page for user | uploded in the server
| Task 3 | Pendios | middle | Rahamath | actions page | resolved the issue