## Sheet1
S No | Main Task | Modules | Start Date | End Date | Remarks | Responsiblity | Remarks 1
1 | Board Bring Up | Board test |  |  |  | Khaleel
|  | GPIO test |  |  | Led Blink | Khaleel
|  | GPIO Out Put test |  |  | All Outputs | Sunil
|  | GPIO Input test |  |  | All Inputs | Sunil
|  | BI Color LED Bring Up |  |  | PWM Technique | Sunil
|  | RS232 |  |  | All Channels | Sunil
|  | Motor Interfacing |  |  | Intefacing with VFD Drives | Khaleel/Sunil
|  | Pneumatic |  |  | On/OFF | Khaleel/Sunil
|  | ADC |  |  | 2 Channel | Khaleel/sunil
|  | CAN |  |  | Only initial working test | Khaleel/Sunil
|  | Camera |  |  | Only initial working test | Khaleel/Sunil
2 | Stage 1 | RS232 |  |  | Computer Communication for GUI Control | Khaleel/Sunil/Mahesh (GUI) | Elevator control, Orientation/ Cutter Operation/ Segregation control operation through Computer GUI
|  | GPIO Inputs |  |  | Proximity Sensor Inputs
|  | GPIO Outputs |  |  | Actuators/Motors/Pneumatic
|  | BI Color LEDS |  |  | Machine Status
3 | Stage 2 | Netwrok of Slaves Devices with Master |  |  | All Slaves and Master is netwroked through RS232 | Khaleel/Sunil/Mahesh (GUI) | User can control any Slave Device using Computer GUI
4 | Stage 3 | Camera Wokring Orientation |  |  | Orientation correction and Mechanical Control | Khaleel/Sunil/Mahesh (GUI) | Full Working of Orientation i.e. Camera, All Mechanical Interfaces
5 | Stage 4 | Camera Pod Detection |  |  | POD detection and Cutter Activation | Khaleel/Sunil/Mahesh (GUI) | Interfacing Encoder and Timing Sequence
6 | Stage 5 | Camera Segregation |  |  | Chilly Quality Detection | Khaleel/Sunil/Mahesh (GUI) | Interfacing the Segregation Mechanism
7 | Stage 6 | Full System Testing |  |  | Raspberry PI GUI | Khaleel/Sunil/Mahesh (GUI) | HTML Drag drop Builder