## Board Bring Up
S No | Main Task | Modules | Start Date | End Date | Remarks | Responsiblity | Remarks 1
1 | Board Bring Up | Board test |  |  |  | Khaleel
|  | GPIO test |  |  | Led Blink | Khaleel
|  | GPIO Out Put test |  |  | All Outputs | Sunil
|  | GPIO Input test |  |  | All Inputs | Sunil
|  | BI Color LED Bring Up |  |  | PWM Technique | Sunil
|  | RS232 |  |  | All Channels | Sunil
|  | Motor Interfacing |  |  | Intefacing with VFD Drives | Khaleel/Sunil
|  | Pneumatic |  |  | On/OFF | Khaleel/Sunil
|  | ADC |  |  | 2 Channel | Khaleel/sunil
|  | CAN |  |  | Only initial working test | Khaleel/Sunil
|  | Camera |  |  | Only initial working test | Khaleel/Sunil
2 | Stage 1 | RS232 |  |  | Computer Communication for GUI Control | Khaleel/Sunil/Mahesh (GUI) | Elevator control, Orientation/ Cutter Operation/ Segregation control operation through Computer GUI
|  | GPIO Inputs |  |  | Proximity Sensor Inputs
|  | GPIO Outputs |  |  | Actuators/Motors/Pneumatic
|  | BI Color LEDS |  |  | Machine Status
3 | Stage 2 | Netwrok of Slaves Devices with Master |  |  | All Slaves and Master is netwroked through RS232 | Khaleel/Sunil/Mahesh (GUI) | User can control any Slave Device using Computer GUI
4 | Stage 3 | Camera Wokring Orientation |  |  | Orientation correction and Mechanical Control | Khaleel/Sunil/Mahesh (GUI) | Full Working of Orientation i.e. Camera, All Mechanical Interfaces
5 | Stage 4 | Camera Pod Detection |  |  | POD detection and Cutter Activation | Khaleel/Sunil/Mahesh (GUI) | Interfacing Encoder and Timing Sequence
6 | Stage 5 | Camera Segregation |  |  | Chilly Quality Detection | Khaleel/Sunil/Mahesh (GUI) | Interfacing the Segregation Mechanism
7 | Stage 6 | Full System Testing |  |  | Raspberry PI GUI | Khaleel/Sunil/Mahesh (GUI) | HTML Drag drop Builder

## Slave Module
S No | Board Type | Module | Sub Modules | Remarks | Team Member
1 | Slave | Camera | Camera Initi ( hw.h) (Hw C)
|  |  | Camer Image Processing (IMF.h) (Camera FilterClass) 1. Gray Scale Converstion 2. Gaussian Filter 3. Sober Filter | To be implemente in 16 Bit Need to consult Anupam for clarification
1. Orentation Detection (Detection.h) ( Detction Class) 2. Pod Detection 3. Quality Detection
2 |  | CAN | CAN initi ( hw.h) (Hw C)
|  |  | Transmitter Receiver Error Check | Make Priority is set as a parameter
CAN Parser 1. Packer Encode 2. Packe Decode
3 |  | VFD Drive Control | Modbus Initi (Modbus.h ) Mobus Class
Jonson Parser
RS232.h ( Hw.h)
Commands ( Fw, Rv, Stp, Speed) Motor.h Motor class
Modbus to RS232 protocol Converter Modbus.h
4 |  | Encoder | Initi Endcoder Pins (Hw.h) hardware Class
QEI function ( encoder.h) Dr, Speed)
5 |  | Penamatic | GPIO init ( hw.h) hardware class
|  |  | ONOFF (Penamatic .h) | Send Penamatic name and Status
6 |  | Sensor | GPIO init ( hw.h) hardware class
|  |  | Read Status (Sensor Name) Sensor.h Sensor Class | Return Senosor Name and Status
7 |  | Error Indication | GPIO init ( hw.h) hardware class
|  |  | LED Coler pattern | Parmater Error Status
8 |  | ADC | ADC init, Hw.h hw Class
Read ADC
Data Conversion
9 |  | Flash Memory | Flash Memory Init, Hw.h Hw Class
|  |  | Read FLashNu.h FlashNu Class | Sector and Block wise operation
Write
Erase
Error Check Read ID, etc
10 |  | Two UASRTs | UART inti hw.h hw class | Name the use case
Read UARTNum.h UARTNu class
Write
Protocol Encode
Protocol Decode
11 |  | Stepper Motor | GPIO init ( hw.h) hardware class
ONOFF (Stepper .h)
Speed Control
Direction Control
12 |  | Application Layer | Check for Switch configuration ( Jumper or Sw Flags)
Call the respective function for Camera
Call the Calculations for Pematic operation
Call the function stepper Motor drive
Commminicate with Master board
read Encoder parameters
Remote Firm Update ( OTA)
Check Sensor Status
13 |  | Commincation to Master/Slave (CAN) | Send command | function to take address to send and the data
Receive Command
Parase Command
Formate command

## Master Board
S No | Board Type | Module | Sub Modules | Remarks | Team Member
1 | Master | CAN | CAN initi ( hw.h) (Hw C)
|  |  | Transmitter Receiver Error Check | Make Priority is set as a parameter
CAN Parser 1. Packer Encode 2. Packe Decode
2 |  | Two UASRTs | UART inti hw.h hw class | Name the use case
Read UARTNum.h UARTNu class
Write
Protocol Encode
Protocol Decode
3 |  | Commincation to Master/Slave (CAN) | Send command | function to take address to send and the data
Receive Command
Parase Command
Formate command
4 |  | Elevator Control | GPIO Init (Modbus)
ON OFF
Sensor Input
Vibration Sensor
Speed Monitor Encoder
5 |  | VFD Drive Control | Modbus Initi (Modbus.h ) Mobus Class
Jonson Parser
RS232.h ( Hw.h)
Commands ( Fw, Rv, Stp, Speed) Motor.h Motor class
Modbus to RS232 protocol Converter Modbus.h

## System Architecture
Raspebrry Pi
33 Kgs / hr
Channle 1 | Channle 2 | Channle 3
Mater Board (Elevator and Slave corodnation with cloud)
Or 1 | Or 2 | Or 3
Pod 1, pod 2, Pod 3 | Pod 1, Pod 2, Pod3 | Pod 1, Pod 2, Pod 3
Q 1, Q 2, Q3 | Q 1, Q 2, Q3 | Q 1, Q 2, Q3