## Peripheral
Task no | Task details | Sub task | Team members | Status | Remarks
CAL1001 | CAN | CAN 1-1 interace
CAN random data send and recieve
CAN Multi node tx and rx
CAN JSON data formation
CAN OP codes for the data and cmds
CAL1002 | QEI | Read Speed/Frequency
Read Direction
Read Position
Set zero position
Calculate the relation with gear ratio value
CAL1003 | Pneumatics | GPIO output with stepper motor terminals
Time to On and Off
CAL1004 | Modbus | Rs232 protocol
Command formation
Modbus protocol function
JSON parsing
CAL1004 | BiColor LED's | Led's gpio output
CAL1005 | Stepper Motor | Stepper motor driving
Variable frequency/speed
Direction change
CAL1006 | Sensor | GPIO input for proximity sensor
CAL1007 | Flash Memory | Read chip info
Read data
write data
erase sector
erase block
erase chip
CAL1008 | UART | UART init
TX and RX data
CAL1009 | Camera Interface | Camera Initialization
Camera device info
Camera capture
object detection
link pod detection with encoder position and speed
camera color detection
Object sorting

## Task and assignment
(Week Sprint 1) 28/Jun/2021 Team lead Sunil, Khaleel Tech Lead | [5 empty] | Time Sheet
|  | Sub Task | Team Member | Complexity Level | Remark | Sunil | Kheeel | Arun | Rhjamatah
Objective 1 | CAN | CAN 1-1 interace | Khaleel | High |  | 8
|  | CAN random data send and recieve | Sunil | Medium |  |  | 3
|  | CAN Multi node tx and rx | Rahamath | Medium |  |  | 2
CAN JSON data formation
CAN OP codes for the data and cmds
Objective 2 | QEI | Read Speed/Frequency
Read Direction
Read Position
Set zero position
|  | Calculate the relation with gear ratio value | [7 empty] | Khaleel
Objective 3 | Pneumatics | GPIO output with stepper motor terminals | [7 empty] | Sunil
|  | Time to On and Off | [7 empty] | Rahamath
Objective 4 | Modbus | Rs232 protocol | [7 empty] | Arun
Command formation
Modbus protocol function
JSON parsing
Objective 5 | BiColor LED's | Led's gpio output
Objective 6 | Stepper Motor | Stepper motor driving | [7 empty] | High
|  | Variable frequency/speed | [7 empty] | Medium
|  | Direction change | [7 empty] | Low
Objective 7 | Sensor | GPIO input for proximity sensor
Objective 8 | Flash Memory | Read chip info
Read data
write data
erase sector
erase block
erase chip
Objective 9 | UART | UART init
TX and RX data
Objective 10 | Camera Interface | Camera Initialization
Camera device info
Camera capture
object detection
link pod detection with encoder position and speed
camera color detection
Object sorting